## Sheet1
Fat Tire Festival 2016 Super-duper Volunteer List
Event | Location | Date | Time 2012 | Position | Task Details | Volunteer Name
Thursday
Jump and Pump Jam 6pm-7:30pm
Jump Jam | Rosemont | 2016-08-25 | 5:30 | Set-up | Registration table, sound system | Jess, Tom Atikins
Jump Jam | Rosemont | 2016-08-25 | 6-7:30 (1.5) | MC jump Jam | MC | Jess
Jump Jam | Rosemont | 2016-08-25 | 6-7:30 (1.5) | Registration Table | Handle registrations for weekend events | Nelson Rocha
Jump Jam | Rosemont | 2016-08-25 | 6-7:30 (1.5) | First Aid |  | Dom Baker
Pump Jam | Rosemont | 2016-08-25 | 6-7:30 (1.5) | Timing at Pump Track | 2 volunteers: 1 to time, one to record names | Travis, Tom Atkins, Moe
Friday
Bike Fest
Bike Fest | Baker | 2016-08-26 | 4:30 | Set-up | Set up tables and tents where needed | Jess
BikeFest | Baker | 2016-08-26 | 5:00–6:00pm | Parade Decorating | Manage decorating table, hand out t-shirts and kids plates - need 2 volleys | NDCC
BikeFest | Baker | 2016-08-26 | 6:00-6:15 pm | Parade Marshalls | 6 Marshals required for stopping traffic at intersections | Tom Atkins, Jamie and Tucker, Oso
BikeFest | Baker | 2016-08-26 | 6:00-7:00 pm | Registration Table | Register people for evening events | Erin Shippy
BikeFest | Baker | 2016-08-26 | 6:00-7:30pm | MC and awards presentation | MC the evening and provide prizes to winners. | Jess (oso help with prizes)
Bike Fest | Baker | 2016-08-26 | 7:30pm | Tear down | Take down tables and tents | Jess
Bike Fest | Baker | 2016-08-26 | 5:00-7:30pm | First Aid | Provide First Aid for the evening | Dom Baker
Saturday
Smallwood Ride
Smallwood Ride | Smallwood | 2015-08-22 | 9am | Ride leader/registration | Lead the ride, provide first aid | Andrew Chewter
Smallwood Ride | Smallwood | 2015-08-22 | 9am | Ride tail gunner/first aid | Tail gun and provide first aid/bike repair support. | Remi Champagne
XC Poker ride
Poker ride XC | Mountain Station | 2016-08-27 | 2:15-5:15 (3) | Set-up and tear down, registration | Set-up tent, table for registration, asssist with registration/ record cards, direct to Royal, tear down | Jess, Travis | Jess to show up with tents, registraton stuff
Poker ride XC | Mountain Station - parking lot | 2016-08-27 | 2:15 - 5:15 (3) | Registration and first card | Register participants | Clancy
Poker ride XC | Mountain Station - | 2016-08-27 | 2:30-5:00 (2.5) | Course marshal/first aid | Provide first aid and first card @ Raccon/Badger intersection | Angie Kalbun
Poker ride XC | Mountain Station - | 2016-08-27 | 2:30-5:00 (2.5) | Course marshal/first aid | Provide second card at the end of Badger | Lindsay Jennings
Poker ride XC | Mountain Station | 2016-08-27 | 2:30-5 | Course marshal/first aid | Provide 3 card at start of Graveyard Trail entrance | Sarah Kemp
Poker Ride XC | Mountain Station - top of Expresso | 2016-08-27 | 2:30-5:00 (2.5) | Course marshal/first aid | Provide fourth card at end of graveyard trail network | Mike Hood
Poker ride XC | Mountain Station | 2016-08-27 | 2:30-5:00 (2.5) | Sweeper | Ride course after everyone else | Clancy, Cari
DH Blackjack ride
Black Jack ride DH shuttle | Goldmember or Powerslave | 2016-08-27 | 10:00-2:30 (4.5) | Registration | Hang out at Sacred Ride: Register participants | Evan, Moe
Black Jack ride DH shuttle |  | 2016-08-27 | 10:00 | Set up Registration | Set up Registration table, tent, food | Jess
Black Jack ride DH shuttle | Goldmember or Powerslave | 2016-08-27 | 11-3 | Ride Shuttle driver | Shuttle participants and provide first card. | Leah, Tash
Roots, Rocks, Rhythm Party
| The Royal | 2016-08-27 | 5:45-7:45 (2) | Host/Hostess - prefer to have 2 people | Take tix, sell tix for draw and raffle | Claudia and Steeve
| The Royal | 2016-08-27 | 6:00-7:00 | Last card and recorder | record results, determine winners | Angie Kalbun
| The Royal | 2016-08-27 | 5:00 | Preparation | Set out draw prizes, help with arranging draw/raffle bucket | Jess
Sunday
Morning Mountain Site Services
Site/ All Events | Morning Mtn. | 2016-08-28 | 7:30am | Set-up | Set-up tents, tables, water, food trailers, music etc. | Jess, Travis, Moe, etc
Site/ All Events | Morning Mtn. | 2016-08-28 | 3:00-4:30 | Tear down | Take down tents, tables, etc | Jess, Travis, Moe,etc
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:30-12:30 (4) | Parking/Directing Traffic, etc | direct traffic for parking | Evan
Registration and Sign In
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:00-1:00 (5) | Check In Table | Greeter; direct to sign in or Registration, give out information/work volley table | Clancy
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:00-11:00 (3) | Registration Table | Registration forms, payment sell t-shirts | Kristin Tedford
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:00-11:00 (3) | Registration Table | Registration forms, payment sell t-shirts | John Doyle
Site/ All Events | Morning Mtn. | 2016-08-28 | 11:00-2:00 (3) | Registration Table | Registration forms, payment sell t-shirts | Gerry Sobie
Site/ All Events | Morning Mtn. | 2016-08-28 | 11:00-2:00 (3) | Registration Table | Registration forms, payment sell t-shirts | Chris Sobie
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:00-11:00 (5) | Sign In Table | Sign people in/ give number plate | Ava
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:00-1:00 (5) | Sign In Table | Sign people in/ give number plate | Lindsay Jennings
Miscellaneous Tasks
Site/ All Events | Morning Mtn. | 2016-08-28 | 3:00-4:00 | Prize presenter/organizer | Prize presenter/organizer | Jess
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:30-2:30 (6) | Volunteer and Draw Table | Direct volunteers; food for volleys. Manage draw prizes | Clancy
Site/ All Events | Morning Mtn. | 2016-08-28 | 8:30-3:30 | Photographer | Take pictures of events
Kids XC
Kids XC | Morning Mtn. | 2016-08-28 | 9:00 - 10:45 (2) | Starter | organize heats; give directions; start races, give out ribbons | Jim Jamieson
Kids XC | Morning Mtn. | 2016-08-28 | 9:00- 10:45 (2) | Finish line | Record names of top 3-5 finishers; clear area of riders -require 2 helpers here | Oso Punchard, Greg Munby
Kids XC | Morning Mtn. | 2016-08-28 | 9:00-10:30 (1.5) | Course Marshal | At loop entrances - need to move after each heat. | Nelson Rocha | Blue, Red, Orange Purple entrances
Kids XC | Morning Mtn. | 2016-08-28 | 9:00-10:30 | Course Marshal | crossings | Cari
Kids XC | Morning Mtn. | 2016-08-28 | 9:00-10:30 | Course Marshal | At the lower corner of Plunger | Blair Weston
Kids XC | Morning Mtn. | 2016-08-28 | 9:00-10:30 | Lead Rider (bunny) | Lead Rider (bunny) | Mike Hood
Kids XC | Morning Mtn. | 2016-08-28 |  | MC | Announce heats, winners | Jess
Enduro Event
Enduro | Morning Mtn. | 2016-08-28 | 11:30-3:30 | Master of Ceremonies
|  |  |  | Start Marshal | give out instructions for chip timing, etc | Travis/Jess
Enduro SANE | Morning Mtn. | 2016-08-28 | 10:30-12:30 (2) | Kootenay Krossing Marshal | Top of Lefty for descent for Sane | Ben Cross
Enduro SANE | Morning Mtn. | 2016-08-28 | 10:30 - 12:30 (2) | Course Marshal/First Aid | Crossing of Bottom's Up on Lefty (end of Stage 1) | Blair Weston
Enduro SANE |  |  | 10:30-1:00 (2.5) | Course Marshal/First Aid | Mid Lefty Somewhere | Craig (First Aid)
Enduro INSANE |  |  | 12:30-2:30 (2) | Kootenay Korner | Kootenay Korner directing traffic up | Ben Cross
Enduro INSANE |  | 2016-08-28 | 12:30-3:00 | Course Marshal/First Aid | Kootenay Korner directing traffic down | Chris Hillary (First Aid)
Enduro INSANE | Morning Mtn. | 2016-08-28 | 12:30-3:30 | Insane Stage 1 Marshal | Top of Turnstyles (end of Stage 3) | Greg and Moe
Enduro INSANE | Morning Mtn. | 2016-08-28 | 12:30-3:30 | Course Marshal/First Aid | Mid Placenta - where it crosses Turnstyles | Christian Rawles
Enduro INSANE | Morning Mtn. | 2016-08-28 | 12:30-3:30 | Course Marshal/First Aid | Placenta turns into Oilcan | Stephan
Enduro INSANE |  |  | 12:30-3:30 | Course Marshal/First Aid | Oilcan crosses Lefty | Craig
Enduro INSANE |  |  | 12:30-3:30 | Course Marshal/First Aid | Unit Crewzer Trail Head | Sheila Street
Enduro | Morning Mtn. | 2016-08-28 | 11:30-4:00 (4.5) | DH Finish Marshal | Ensure participants go through finish; take transponders | Ava
Enduro | Morning Mtn. | 8/28.2016 |  |  | Sweeper | Greg Munby | run up to close Placenta from Give out; take transponder up
|  |  |  | EMAIL US AT | NELSONFATTIRE@GMAIL.COM | TO HELP!